RRC Catchment Restoration Fund monitoring protocol

Key:

- Target/why – What is the overall objective of the works which are to be monitored?

- What – What are you trying to observe from your monitoring? E.g. increased sinuosity and habitat heterogeneity through re-meandering and adding large wood / reduction in nutrient inputs by installing SuDS.

- How – What techniques are being used to collect data and what assessment methods are you using? E.g. electro-fishing monitoring diversity, abundance, density, length and age.

- When – When are you collecting data (month/season)? Duration/length of monitoring period, how many sampling repeats, how regularly?

- Who – Who is the individual and/or organisation responsible for monitoring? Will this be done by more than one organisation?

- Data – Do you have access to any pre-project data? E.g. monitoring data from the Environment Agency.

- Cost – Cost of monitoring. Are all costs in kind, or are there expenditures for e.g. external lab analysis.

- Which WFD objective is this helping to achieve – Which WFD quality element will be addressed by your works? If not WFD, does the work/undertaking aim to improve favourable conditions (for designated sites or species, e.g. SSSI/SAC/SPA/BAP) or does it relate to any other policy drivers (e.g. public engagement, socio-economics, flood management, ecosystem services)

- Priority and confidence: 
Priority: High/Medium/Low importance that your monitoring method can show potential improvement of the related WFD quality element; the favourable condition (i.e. designated site or species such as SSSI, SAC, SPA, BAP); and/or other policy drivers (e.g. socio-economics, flood management, ecosystem services).
Confidence: High/Medium/Low confidence that the monitoring is robust, suitable and has the potential to show what you are trying to observe within the CRF project time limit.

| Target/Why What is the overall objective of the works which are to be monitored? | What What are you trying to observe from your monitoring? | How What methods are you going to use? | When What periods over the year and how often? (to indicate variability) And where if possible | Who Who is going to do this? | Data What existing data is available in addition to the monitoring being outlined here | Cost (can be in kind) | Which WFD quality element is this helping to achieve? If not WFD specify (e.g. SSSI, SAC, BAP or other policy driver) | Priority High/medium/low linked to WFD or other designation | On target Are the monitoring tasks outlined running to schedule? (if no specify) NOTE- can use RRC update questionnaires as a start. | Key reporting tool and reporting output |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Confidence High/medium/low robustness of monitoring |  |  |
| Will be different for each project – what is the project aim for the area being photographed? | A visual change in (please specify) as a result of (please specify) | Fixed point photography – for methodology, refer to RRC’s Practical river monitoring guidance (2011) X number of photos (state if known) & indicate if RRC have been provided with a map of points (Y/N) | E.g. Before, immediately after and post works recommended (state dates if known, e.g. month and year) | Project team/ Volunteers | State if fixed point photography or any anecdotal/ ad-hoc photography prior to CRF | Through project/ In-kind | State which of the following, the FPP demonstrates: a) WFD targets, b) designated river or c) other e.g. social science targets | Priority: Please state (only grey if High) | Yes/ No | A time-series of fixed point photographs State if any other analysis is being done |
|  |  |  |  |  |  |  |  | Confidence: Please state (only grey if High) |  |  |

- On target – Are the monitoring tasks outlined running to schedule? If no, why not?

- Reporting tool and reporting output – How will your collected monitoring data be recorded and the analysis outputs reported?

Example of Fixed Point Photography:

| Target/Why What is the overall objective of the works which are to be monitored? | What What are you trying to observe from your monitoring? | How What methods are you going to use? | When What periods over the year and how often? (to indicate variability) And where if possible | Who Who is going to do this? | Data What existing data is available in addition to the monitoring being outlined here | Cost (can be in kind) | Which WFD quality element is this helping to achieve? If not WFD specify (e.g. SSSI, SAC, BAP or other policy driver) | Priority High/medium/low linked to WFD or other designation | On target Are the monitoring tasks outlined running to schedule? (if no specify) NOTE- can use RRC update questionnaires as a start. | Key reporting tool and reporting output |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Confidence High/medium/low robustness of monitoring |  |  |
| A visual improvement in the two brooks after river works | - Naturalise 400m Mad Brook (restoring historic meandering route) - Increase in flood storage through reedbed creation in the Lyde Brook | Fixed point photography (focus on channel change and vegetation growth) | Before & after works in December 2013 and throughout 2014. | M.Sc. student | Ad hoc historic photography | In-kind | Hydromorphology, ‘Not assessed’ but almost certainly ‘not Good’ in Waterbody ID GB109054050280 (Mad Brook) & Waterbody ID GB109054049530 (Lyde Brook) | Priority: High | Yes | Report including an analysis of the photo results |
|  |  |  |  |  |  |  |  | Confidence: High |  |  |
| Detect changes in the biota of Mad Brook and Lyde Brook | Change in macroinvertebrate communities | Kick-sampling for 1 min, sorted by hand from white tray – asses taxonomic group at each project site 2 control sites (SSSI site – 1 site, no works) & 1 site D/S | Baseline survey - February 2013. One kick-sample per month in each brook from March 2013 – March 2014 Local group will maintain and monitor the site long-term. | Volunteer monitoring team (trained, local group); M.Sc. student (analysis) | Existing EA macroinvertebrate dataset (separate sample sites, within same waterbodies) | In-kind(trained volunteers) | Invertebrates – Bad in both Waterbody ID GB109054050280 (Mad Brook) & Waterbody ID GB109054049530 (Lyde Brook) | Priority: High | Yes | Report including an analysis of Biological Monitoring Working Party score (BMWP) – to indicate water quality & proxy for river habitat improvements. |
|  |  |  |  |  |  |  |  | Confidence: High |  |  |
| Detect changes in the water chemistry of Mad Brook and Lyde Brook | Change in Nitrate, Ammonia, Phosphate, PH, Temperature, Conductivity, Turbidity and Dissolved oxygen | Standard method of water sampling to be collected by hand from defined points on both brooks (at project sites or strategic). Bankside sampling predominantly. | Baseline survey in February 2013. One visit per month in each brook from March 2013 – March 2014 Local group will maintain and monitor the site long-term. | Volunteer monitoring team (trained, local group); M.Sc. student (analysis) | Existing EA water chemistry dataset | In-kind(trained volunteers) sampling and | Dissolved Oxygen – Moderate in Waterbody ID GB109054050280 (Mad Brook) & High in Waterbody ID GB109054049530 (Lyde Brook) | Priority: High | Yes | Report including an analysis of the water chemistry results |
|  |  |  |  |  |  |  |  | Confidence: High |  |  |
| Increase in public awareness of the need to look after rivers | Active involvement of local communities and school children | 8 community events and school activities; 10 volunteer training & activity days in water sampling and biological surveying; Dissemination of materials for local schools & groups | Programme ties in with school year – events throughout 2012-2015 | Shropshire Wildlife Trust staff | None | Through project | Project objective – Encourage aftercare of waterways by local community | Priority: Medium (project objective only) | Yes | Shropshire Wildlife Trust to report on these |
|  |  |  |  |  |  |  |  | Confidence: High |  |  |
| Increase in business sector awareness of the need to look after waterways | Engagement with businesses in local area, specifically, Telford | Reach 120 Telford Businesses by discussing water quality issues and pollution through the local BESST business network, via 2 engagement forums; & 2 employee volunteering sessions | Creation and ongoing running of a network scheme with businesses – real beneficial outcome of the project to date. | Shropshire Wildlife Trust staff | None | Through project (and in-kind from BESST volunteers) | WFD – N/A Project objective – Encourage aftercare of waterways by local businesses | Priority: Medium (project objective only) | Yes | Shropshire Wildlife Trust to report on these |
|  |  |  |  |  |  |  |  | Confidence: High |  |  |
| Monitor and demonstrate effectiveness of a new Sustainable Urban Drainage (SUDs) system on the Ricoh business site, Telford | Retention of water in the drainage basin (SUDSs); Education about SUDs and uptake. | Fixed point photography (at demonstration site) | A programme of monitoring ties in with practical actions being undertaken. | Shropshire Wildlife Trust staff | Halfron technical note and feasibility study (details existing drainage, flow attenuation calculations and the chosen SUDs option | Through project | Project objective – To develop an exemplar Sustainable Urban Drainage system on a business site in Telford | Priority: Medium (project objective only) | Yes | Shropshire Wildlife Trust to report on these |
|  |  |  |  |  |  |  |  | Confidence: High |  |  |
| Detect change in ecology of Mad Brook and Lyde Brook using bats and herptofauna as proxy species | Change in suitability of habitat/ potential for bats and herptofauna (amphibians and reptiles) | Pre-works ecology baseline survey Bat identification using detectors (volunteers trained by bat specialists) Training sessions around how watercourse management affect different ecological species. | Throughout the CRF programme (Mad Brook will tie in with volunteer sessions at the Local Nature Reserve site. On Lyde Brook, it will depend on how proactive the volunteers are). | Volunteer led monitoring programmes | Pre-works ecology survey (Phase 1). SWT utilised the SWT consultants branch & this covered mammals, bats etc. | In-kind(trained volunteers) | Secondary project objective – to improve riparian habitat conditions for fauna in both catchments in a range of different habitats (wet woodland, ponds, reed bed, brooks) | Priority: Low (other ecological surveys) | Yes | Habitat suitability index score List of bats identified – there is a species scoring system. Shropshire Wildlife Trust to report on these |
|  |  |  |  |  |  |  |  | Confidence: Low (repeat ecology survey not confirmed; other monitoring depends on how proactive volunteers are on Lyde Brook) |  |  |